## RTMs
Use Case Description | Test Case ID | Test Case Description | Test Step | Expected Results | Results per Step | Overall Result | QA Remark
Add to cart | TC001 | Verify Badge with counter elements
| TC002 | Display counter badge only when there are items
| TC003 | Verify cart dropdown visibility
| TC004 | Verify cart dropdown visibility when a product is added to cart
| TC005 | Verify all items are cleared on clicking clear button
| TC006 | Verify when a product is added twice quanity increases
Pagination | TC001 | Verify Pagination Visibility
| TC002 | Verify 6 items per page
| TC003 | Verify only current page is seen on moving through various pages
| TC004 | Verify Previous Button is not visible on First Pages
| TC005 | Verify Next Button is not visible on Last Page
Products | TC001 | Verify 6 products are displayed
| TC002 | Veridy Add to Cart bar on hover
| TC003 | Verify Product Price
| TC004 | Veridy Price Currency
| TC005 | Verify each product has images
Sorting | TC001 | Verify two types of sorting are available
| TC002 | Verify arrows change the order of sorting
Filtering | TC001 | Verify Products should be filterable
| TC002 | Verify products can be filtered by mulitple categories
| TC003 | Verify products can be filtered by price
| TC004 | Verify filter by Categories and Price
| TC005 | Veriify on no matches found "No Results" is displayed
| TC006 | Verify filters affect pagination

## Defects
Open Defects
Defect ID | Subject | QA Remarks | Detected ON | Status | Developer Remarks | Priority | Severity
1 | Product on Last page in Pagination | The Product display in the last page in pagination is not displayed properly Expected all the divs to be with the same properties despite its page position | 2022-06-16 | Open |  | High | Major
2 | Product List Per Page | Expected products per page is six but only four are displayed | 2022-06-16 | Open |  | Medium | Medium
3 | Counter Badge on Add to Cart | The counter badge is shown even without an item in the cart | 2022-06-16 | Open |  | Medium | Low

## Sheet1
Open | High | Critical
Closed | Medium | Major
Resolved | Low | Medium
Rejected |  | Low
Reopen